TRAVENTIONS Weekly Status Report – Implementation 17th April 2025

Status update for the period from Week 1 (23 March 2026) to Week 4 (17 April 2026):

KEY MILESTONES

| Key Milestone | Date |
| --- | --- |
| Project Kick-Off | 23rd March |
| Planning | 23rd March |
| Handover | — |
| SignOff & CSAT | — |

| Change Request # | Status |
| --- | --- |
| Nil | — |

CHANGE REQUESTS

| OVERALL STATUS All Milestones; Date; %. Project Kick-Off; 23rd March; 100%. Planning; 23rd March; 100%. Core Modules Development; —; 75%. Flight Booking Module; —; 85%. Ticketing System; —; 80%. Admin Panels; —; 0%. Cab & Hotel Modules; —; 0%. Overall Progress; —; ~40%. Overall Status: AMBER — Project is in Amber status due to delays in external API integration and pending infrastructure credentials. Core modules are completed and stable. Remaining work is focused on integrations, admin panels, and advanced booking features.. |  |
| --- | --- |

| Accomplishments Till Date - Completed TMC Registration Module with 4-step verification flow - Implemented Login with 2FA (Authentication System) - Developed TMC Support Agent setup with ticket handling & internal notes - Built Ticketing UI system (priority assignment, categorization, description) - Implemented Flight Booking Module – core features (one-way, round trip, filters) - Established Technical Architecture: Monorepo (Turborepo + pnpm + TypeScript) | Planned tasks for the upcoming phase - Implement Refund tracking & cancellation confirmation workflows - Develop Admin Panels: TMC Admin, Booking Agent Interface, Super Admin - Integrate AWS credentials & configure external API keys - Resolve passenger data state persistence issue - Fix edit page frontend-backend binding bug - Begin AWS SES integration for OTP email authentication |
| --- | --- |

Deviation Points

- Delay due to unavailability of Amadeus enterprise API key – integration complexity higher than estimated

- Pending AWS credentials blocking TMC Registration enhancements and OTP email functionality

- Admin panels and Cab & Hotel booking modules yet to begin development

RISKS

| S.No | Risk | Mitigation | Category | Owner | Reported Date | Target Resolution | Status | Closed Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Amadeus API integration complexity (enterprise API key unavailable) | API optimization & fallback handling | Technical | Dev Team | Ongoing | ASAP | Open | — |
| 2 | Missing AWS credentials blocking registration enhancements | Follow-up with stakeholders | Dependency | Client | Ongoing | ASAP | Open | — |
| 3 | Flexible pricing data limitation | Custom transformation logic | Technical | Dev Team | Ongoing | Next Sprint | Open | — |

ISSUES

| S.No | Issue | Action Plan | Category | Owner | Reported Date | Target Resolution | Status | Closed Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Passenger data not persisting across booking steps | Fix state handling & API sync | Functional | Dev Team | Ongoing | This Week | In Progress | — |
| 2 | Edit page not reflecting updates | Debug frontend-backend binding | UI/Backend | Dev Team | Ongoing | This Week | In Progress | — |
| 3 | OTP email not implemented | Integrate AWS SES | Integration | Dev Team | Ongoing | Next Sprint | Open | — |
| 4 | General bugs across modules | Continuous testing & fixes | QA | Dev Team | Ongoing | Continuous | In Progress | — |