## Clarifications
Point | Area | Client Input | Concern / Gap | Clarification Required
1 | Flight Supply Integration | Use Amadeus + external APIs | Free Amadeus API deprecated | Confirm provision of Amadeus Enterprise API credentials
2 | Payment Gateway Routing | USD, SAR, INR gateways | Scope unclear | Confirm if only USD, SAR, INR required or more currencies planned
3 | Currency Conversion Module | Internal custom module | Insufficient technical details | Provide detailed logic, rules, rate updates, audit expectations
4 | Margin Manager Module | Multi-level margins | Highly critical but underspecified | Provide detailed functional specs, workflows, approval logic
5 | Domain & Integrations | Traventions.com | Access not provided | Provide domain console access, 2FA setup (SES/SendGrid), payment gateway credentials
6 | Official MVP boundary | The overall direction is clear, but the exact list of phase-one deliverables is not frozen across the notes. | Needs confirmation | Please confirm the official MVP or phase-one boundary.
7 | Module mix for launch | Flights are clearly central; hotels and transfers remain in scope direction but may not be equally mature. | Needs confirmation | Please confirm whether launch is flights only, flights plus hotels, or a broader combination.
8 | Supplier strategy | Both direct integrations and aggregator or hub-led access have been discussed. | Evolving | Please confirm whether the preferred approach is direct, aggregator-led, or hybrid.
9 | Priority flight APIs | Several GDS or supplier names have been mentioned, but the first implementation list is not fully locked. | Needs confirmation | Please confirm the phase-one priority list.
10 | Hotel scope | Dynamic suppliers, static contracts, and manual confirmation workflows have all been discussed. | Evolving | Please confirm what is mandatory in the MVP.
11 | Transfers / rent-a-car | Included in direction, but less functionally detailed than flights and hotels. | Needs confirmation | Please confirm if this remains part of the MVP.
12 | Wallet / credit / billing | Repeatedly discussed, but some later conversations suggest parts may move to phase two. | Evolving | Please confirm what goes live in phase one and what is deferred.
13 | Payment gateway scope | Gateway integration is discussed, but the mandatory live methods are not frozen. | Needs confirmation | Please confirm which payment methods must go live initially.
14 | Role matrix | Three-role and broader multi-role structures have both been referenced. | Needs confirmation | Please confirm the first-release access model.
15 | Support and ticketing | Both basic internal workflows and richer support mechanisms have been discussed. | Evolving | Please confirm the MVP expectation.
16 | Timelines and effort | References include ~2,000 hours, ~2,200 hours, 2,200–2,500 hours, and a 2–4 month MVP or PoC direction. | Needs confirmation | Please confirm the latest valid effort and timeline.
17 | Refund / cancellation automation | There is recognition that some exception flows may remain partly manual. | Needs confirmation | Please confirm the intended automation depth.
18 | Currency, compliance, and documentation | Multi-currency, KYC, and per-country documentation have been discussed, but the first-priority regions and submission rules need to be locked. | Needs confirmation | Please confirm the first-priority countries and compliance requirements.